## Task Data
ID | Phase | Task | Assignee | Role | Start | End | Days | Predecessor | Dep Type | % Complete | Status | Priority | Milestone | Notes
1 | Planning | Project Kickoff Meeting | Sarah Chen | Project Manager | 2026-04-06 | 2026-04-06 | 1 |  |  | 0% | Complete | High | Yes | Align stakeholders on scope and timeline
2 | Planning | Gather Requirements from Department Leads | Sarah Chen | Project Manager | 2026-04-07 | 2026-04-11 | 5 | 1 | FS | 100% | Complete | High |  | Interviews with 6 department leads
3 | Planning | Define Project Scope Document | Sarah Chen | Project Manager | 2026-04-14 | 2026-04-16 | 3 | 2 | FS | 100% | Complete | High |  | Includes budget constraints and success criteria
4 | Planning | Identify Vendor Shortlist | Marcus Rivera | Procurement Lead | 2026-04-14 | 2026-04-18 | 5 | 2 | FS | 100% | Complete | Medium |  | Minimum 3 vendors per category
5 | Planning | Scope Approval | Sarah Chen | Project Manager | 2026-04-17 | 2026-04-17 | 1 | 3 | FS | 100% | Complete | High | Yes | Sign-off from VP Operations
6 | Discovery | Audit Current Infrastructure | James Okoro | IT Lead | 2026-04-21 | 2026-04-30 | 8 | 5 | FS | 100% | Complete | High |  | Server room and network inventory
7 | Discovery | Audit Current Workflows and Pain Points | Sarah Chen | Project Manager | 2026-04-21 | 2026-04-25 | 5 | 5 | FS | 100% | Complete | Medium |  | Document manual processes and bottlenecks
8 | Discovery | Data Migration Assessment | James Okoro | IT Lead | 2026-05-01 | 2026-05-09 | 7 | 6 | FS | 85% | In Progress | High |  | Estimate volume and complexity of data to migrate
9 | Discovery | Vendor Demos and Evaluation | Marcus Rivera | Procurement Lead | 2026-04-28 | 2026-05-09 | 10 | 4 | FS | 70% | In Progress | High |  | Scorecard evaluation across cost and capability
10 | Discovery | Risk Assessment and Mitigation Plan | Sarah Chen | Project Manager | 2026-05-05 | 2026-05-09 | 5 | 7 | FS | 60% | In Progress | High |  | Identify top 10 risks with mitigation owners
11 | Discovery | Discovery Phase Complete | Sarah Chen | Project Manager | 2026-05-12 | 2026-05-12 | 1 | 8,9,10 | FS | 0% | Not Started | High | Yes | Gate review before design phase begins
12 | Design | System Architecture Design | James Okoro | IT Lead | 2026-05-13 | 2026-05-23 | 9 | 11 | FS | 0% | Not Started | High |  | Cloud vs on-prem decision and network topology
13 | Design | Database Schema Design | Priya Patel | Data Engineer | 2026-05-13 | 2026-05-21 | 7 | 11 | FS | 0% | Not Started | High |  | Normalize tables and define relationships
14 | Design | UI/UX Wireframes | Angela Torres | UX Designer | 2026-05-13 | 2026-05-27 | 11 | 11 | FS | 0% | Not Started | Medium |  | Desktop and mobile layouts for 8 core screens
15 | Design | API Integration Mapping | James Okoro | IT Lead | 2026-05-26 | 2026-06-03 | 7 | 12 | FS | 0% | Not Started | High |  | Define endpoints for 4 external systems
16 | Design | Reporting and Dashboard Requirements | Priya Patel | Data Engineer | 2026-05-22 | 2026-05-29 | 6 | 13 | FS | 0% | Not Started | Medium |  | KPIs and refresh frequency for 12 dashboards
17 | Design | Security and Compliance Review | Marcus Rivera | Procurement Lead | 2026-05-26 | 2026-05-30 | 5 | 12 | FS | 0% | Not Started | High |  | SOC 2 and GDPR alignment check
18 | Design | Design Review and Approval | Sarah Chen | Project Manager | 2026-06-04 | 2026-06-05 | 2 | 14,15,16,17 | FS | 0% | Not Started | High | Yes | Architecture board sign-off required
19 | Build | Environment Setup (Dev/Staging/Prod) | James Okoro | IT Lead | 2026-06-08 | 2026-06-12 | 5 | 18 | FS | 0% | Not Started | High |  | Provision cloud resources and CI/CD pipelines
20 | Build | Core Database Build | Priya Patel | Data Engineer | 2026-06-08 | 2026-06-19 | 10 | 18 | FS | 0% | Not Started | High |  | Build tables and stored procedures and indexes
21 | Build | Backend API Development | James Okoro | IT Lead | 2026-06-15 | 2026-07-03 | 15 | 19 | FS | 0% | Not Started | High |  | RESTful services for all core modules
22 | Build | Frontend Development Sprint 1 | Angela Torres | UX Designer | 2026-06-15 | 2026-06-26 | 10 | 19 | FS | 0% | Not Started | High |  | Authentication and navigation and dashboard shell
23 | Build | ETL Pipeline Development | Priya Patel | Data Engineer | 2026-06-22 | 2026-07-03 | 10 | 20 | FS | 0% | Not Started | High |  | Data migration scripts and scheduled refresh jobs
24 | Build | Frontend Development Sprint 2 | Angela Torres | UX Designer | 2026-06-29 | 2026-07-10 | 10 | 22 | FS | 0% | Not Started | Medium |  | Data entry forms and reporting views
25 | Build | API Integration Build | James Okoro | IT Lead | 2026-07-06 | 2026-07-17 | 10 | 21 | FS | 0% | Not Started | High |  | Connect to Salesforce and payment gateway and email service and calendar
26 | Build | Notification and Alerting System | James Okoro | IT Lead | 2026-07-06 | 2026-07-14 | 7 | 21 | SS | 0% | Not Started | Medium |  | Email and Slack and in-app notification triggers
27 | Build | Report and Dashboard Build | Priya Patel | Data Engineer | 2026-07-06 | 2026-07-17 | 10 | 23 | FS | 0% | Not Started | Medium |  | Build 12 dashboards with drill-down capability
28 | Build | Core Build Complete | Sarah Chen | Project Manager | 2026-07-17 | 2026-07-17 | 1 | 24,25,26,27 | FS | 0% | Not Started | High | Yes | All modules feature-complete for testing
29 | Testing | Unit Testing and Code Review | James Okoro | IT Lead | 2026-07-20 | 2026-07-24 | 5 | 28 | FS | 0% | Not Started | High |  | Minimum 80% code coverage target
30 | Testing | Integration Testing | Priya Patel | Data Engineer | 2026-07-20 | 2026-07-28 | 7 | 28 | FS | 0% | Not Started | High |  | End-to-end data flow validation across all systems
31 | Testing | User Acceptance Testing (UAT) | Sarah Chen | Project Manager | 2026-07-28 | 2026-08-07 | 9 | 29,30 | FS | 0% | Not Started | High |  | Test scripts executed by 10 business users
32 | Testing | Performance and Load Testing | James Okoro | IT Lead | 2026-07-28 | 2026-08-04 | 6 | 29 | FS | 0% | Not Started | Medium |  | Simulate 500 concurrent users
33 | Testing | Security Penetration Testing | Marcus Rivera | Procurement Lead | 2026-07-28 | 2026-08-01 | 5 | 29 | FS | 0% | Not Started | High |  | Third-party vendor engagement
34 | Testing | Bug Fix Sprint | James Okoro | IT Lead | 2026-08-10 | 2026-08-19 | 8 | 31 | FS | 0% | Not Started | High |  | Prioritize critical and high severity defects
35 | Testing | Regression Testing | Priya Patel | Data Engineer | 2026-08-20 | 2026-08-26 | 5 | 34 | FS | 0% | Not Started | High |  | Validate all fixes without new defects introduced
36 | Testing | UAT Sign-Off | Sarah Chen | Project Manager | 2026-08-27 | 2026-08-27 | 1 | 35 | FS | 0% | Not Started | High | Yes | Business owner approval to proceed to deployment
37 | Deployment | Production Environment Prep | James Okoro | IT Lead | 2026-08-28 | 2026-09-02 | 4 | 36 | FS | 0% | Not Started | High |  | Final configuration and SSL certs and DNS routing
38 | Deployment | Data Migration (Production) | Priya Patel | Data Engineer | 2026-09-03 | 2026-09-09 | 5 | 37 | FS | 0% | Not Started | High |  | Full data load with validation checksums
39 | Deployment | End User Training Sessions | Sarah Chen | Project Manager | 2026-09-03 | 2026-09-11 | 7 | 37 | SS | 0% | Not Started | High |  | 4 sessions covering all user roles
40 | Deployment | Create User Documentation and SOPs | Angela Torres | UX Designer | 2026-09-03 | 2026-09-11 | 7 | 37 | SS | 0% | Not Started | Medium |  | Quick-start guides and video walkthroughs
41 | Deployment | Go-Live Deployment | James Okoro | IT Lead | 2026-09-12 | 2026-09-12 | 1 | 38,39,40 | FS | 0% | Not Started | High | Yes | Production cutover with rollback plan ready
42 | Deployment | Post Go-Live Monitoring (48 hr) | James Okoro | IT Lead | 2026-09-14 | 2026-09-15 | 2 | 41 | FS | 0% | Not Started | High |  | War room staffed for immediate issue resolution
43 | Closeout | Hypercare Support Period | James Okoro | IT Lead | 2026-09-16 | 2026-10-01 | 12 | 42 | FS | 0% | Not Started | Medium |  | Dedicated support for first 2 weeks post-launch
44 | Closeout | Post-Implementation Review | Sarah Chen | Project Manager | 2026-10-02 | 2026-10-06 | 3 | 43 | FS | 0% | Not Started | Medium |  | Lessons learned and performance vs KPIs
45 | Closeout | Knowledge Transfer to Support Team | James Okoro | IT Lead | 2026-10-02 | 2026-10-08 | 5 | 43 | FS | 0% | Not Started | Medium |  | Runbooks and escalation procedures and access handoff
46 | Closeout | Final Project Report and Sign-Off | Sarah Chen | Project Manager | 2026-10-09 | 2026-10-10 | 2 | 44,45 | FS | 0% | Not Started | High | Yes | Executive summary with budget vs actual and next steps
47 | Closeout | Project Complete | Sarah Chen | Project Manager | 2026-10-10 | 2026-10-10 | 1 | 46 | FS | 0% | Not Started | High | Yes | Archive project files and close project

## Gantt Chart
[6 empty] | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  |  | July 2026 |  |  |  | August 2026 |  |  |  |  | September 2026 |  |  |  | October 2026
[6 empty] | Apr 06 | Apr 13 | Apr 20 | Apr 27 | May 04 | May 11 | May 18 | May 25 | Jun 01 | Jun 08 | Jun 15 | Jun 22 | Jun 29 | Jul 06 | Jul 13 | Jul 20 | Jul 27 | Aug 03 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 07 | Sep 14 | Sep 21 | Sep 28 | Oct 05 | Oct 12
ID | Phase | Task | Assignee | Status | Progress
PLANNING
1 |  | ◆ Project Kickoff Meeting | Sarah Chen | Complete | 0% | bar: April 2026 Apr 06
2 |  | Gather Requirements from Department Leads | Sarah Chen | Complete | 100%
3 |  | Define Project Scope Document | Sarah Chen | Complete | 100% | bar: April 2026 Apr 13
4 |  | Identify Vendor Shortlist | Marcus Rivera | Complete | 100%
5 |  | ◆ Scope Approval | Sarah Chen | Complete | 100% | bar: April 2026 Apr 13
DISCOVERY
6 |  | Audit Current Infrastructure | James Okoro | Complete | 100% | bar: April 2026 Apr 20 to April 2026 Apr 27
7 |  | Audit Current Workflows and Pain Points | Sarah Chen | Complete | 100%
8 |  | Data Migration Assessment | James Okoro | In Progress | 85% | bar: April 2026 Apr 27 to May 2026 May 04
9 |  | Vendor Demos and Evaluation | Marcus Rivera | In Progress | 70%
10 |  | Risk Assessment and Mitigation Plan | Sarah Chen | In Progress | 60% | bar: May 2026 May 04
11 |  | ◆ Discovery Phase Complete | Sarah Chen | Not Started | 0% | bar: April 2026 Apr 06 to October 2026 Oct 12
DESIGN
12 |  | System Architecture Design | James Okoro | Not Started | 0%
13 |  | Database Schema Design | Priya Patel | Not Started | 0% | bar: May 2026 May 11 to May 2026 May 18
14 |  | UI/UX Wireframes | Angela Torres | Not Started | 0%
15 |  | API Integration Mapping | James Okoro | Not Started | 0% | bar: May 2026 May 25 to June 2026 Jun 01
16 |  | Reporting and Dashboard Requirements | Priya Patel | Not Started | 0%
17 |  | Security and Compliance Review | Marcus Rivera | Not Started | 0% | bar: May 2026 May 25
18 |  | ◆ Design Review and Approval | Sarah Chen | Not Started | 0% | bar: April 2026 Apr 06 to October 2026 Oct 12
BUILD
19 |  | Environment Setup (Dev/Staging/Prod) | James Okoro | Not Started | 0%
20 |  | Core Database Build | Priya Patel | Not Started | 0% | bar: June 2026 Jun 08 to June 2026 Jun 15
21 |  | Backend API Development | James Okoro | Not Started | 0%
22 |  | Frontend Development Sprint 1 | Angela Torres | Not Started | 0% | bar: June 2026 Jun 15 to June 2026 Jun 22
23 |  | ETL Pipeline Development | Priya Patel | Not Started | 0%
24 |  | Frontend Development Sprint 2 | Angela Torres | Not Started | 0% | bar: June 2026 Jun 29 to July 2026 Jul 06
25 |  | API Integration Build | James Okoro | Not Started | 0%
26 |  | Notification and Alerting System | James Okoro | Not Started | 0% | bar: July 2026 Jul 06 to July 2026 Jul 13
27 |  | Report and Dashboard Build | Priya Patel | Not Started | 0%
28 |  | ◆ Core Build Complete | Sarah Chen | Not Started | 0% | bar: July 2026 Jul 13
TESTING
29 |  | Unit Testing and Code Review | James Okoro | Not Started | 0% | bar: July 2026 Jul 20
30 |  | Integration Testing | Priya Patel | Not Started | 0%
31 |  | User Acceptance Testing (UAT) | Sarah Chen | Not Started | 0% | bar: July 2026 Jul 27 to August 2026 Aug 03
32 |  | Performance and Load Testing | James Okoro | Not Started | 0%
33 |  | Security Penetration Testing | Marcus Rivera | Not Started | 0% | bar: July 2026 Jul 27
34 |  | Bug Fix Sprint | James Okoro | Not Started | 0%
35 |  | Regression Testing | Priya Patel | Not Started | 0% | bar: August 2026 Aug 17 to August 2026 Aug 24
36 |  | ◆ UAT Sign-Off | Sarah Chen | Not Started | 0% | bar: April 2026 Apr 06 to October 2026 Oct 12
DEPLOYMENT
37 |  | Production Environment Prep | James Okoro | Not Started | 0%
38 |  | Data Migration (Production) | Priya Patel | Not Started | 0% | bar: August 2026 Aug 31 to September 2026 Sep 07
39 |  | End User Training Sessions | Sarah Chen | Not Started | 0%
40 |  | Create User Documentation and SOPs | Angela Torres | Not Started | 0% | bar: August 2026 Aug 31 to September 2026 Sep 07
41 |  | ◆ Go-Live Deployment | James Okoro | Not Started | 0% | bar: April 2026 Apr 06 to October 2026 Oct 12
42 |  | Post Go-Live Monitoring (48 hr) | James Okoro | Not Started | 0% | bar: September 2026 Sep 14
CLOSEOUT
43 |  | Hypercare Support Period | James Okoro | Not Started | 0% | bar: September 2026 Sep 14 to September 2026 Sep 28
44 |  | Post-Implementation Review | Sarah Chen | Not Started | 0%
45 |  | Knowledge Transfer to Support Team | James Okoro | Not Started | 0% | bar: September 2026 Sep 28 to October 2026 Oct 05
46 |  | ◆ Final Project Report and Sign-Off | Sarah Chen | Not Started | 0% | bar: April 2026 Apr 06 to October 2026 Oct 12
47 |  | ◆ Project Complete | Sarah Chen | Not Started | 0% | bar: October 2026 Oct 05
LEGEND
|  | Planning |  | Remaining
|  | Discovery |  | Remaining
|  | Design |  | Remaining
|  | Build |  | Remaining
|  | Testing |  | Remaining
|  | Deployment |  | Remaining
|  | Closeout |  | Remaining
Complete
In Progress
Not Started
| ◆ | Milestone

## Summary
PROJECT SUMMARY DASHBOARD
Metric | Value
Total Tasks | 47
Completed | 7
In Progress | 3
Not Started | 37
Milestones | 9
Overall Progress | 17.34%
PHASE BREAKDOWN
Phase | Tasks | Complete | In Progress | Not Started | Avg Progress
Planning | 5 | 5 | 0 | 0 | 80%
Discovery | 6 | 2 | 3 | 1 | 69.17%
Design | 7 | 0 | 0 | 7 | 0%
Build | 10 | 0 | 0 | 10 | 0%
Testing | 8 | 0 | 0 | 8 | 0%
Deployment | 6 | 0 | 0 | 6 | 0%
Closeout | 5 | 0 | 0 | 5 | 0%
TEAM WORKLOAD
Assignee | Tasks | Total Days | Avg Progress
Angela Torres | 4 | 38 | 0%
James Okoro | 16 | 111 | 11.56%
Marcus Rivera | 4 | 25 | 42.5%
Priya Patel | 8 | 60 | 0%
Sarah Chen | 15 | 47 | 30.67%